## Sheet1
Time Tracking
Date | Time In | Time Out | Total Time | Work Type | Sprint | Description | Sprint Total Hours
2019-01-29 | 17:50 | 20:10 | 2:20 | Research | Sprint 1 | Researched Github/Tools/Libraries | Sprint 1 | 21:54
2019-01-30 | 14:15 | 18:05 | 3:50 | Research | Sprint 1 | Ruby/Ruby API Tutorials | Sprint 2 | 12:05
2019-02-03 | 12:00 | 13:26 | 1:26 | Research | Sprint 1 | Comparing FxRuby To Visual Ruby | Sprint 3 | 13:28
2019-02-04 | 15:00 | 17:43 | 2:43 | Research | Sprint 1 | Bitmaps, rastor vs Vector imaging, | Sprint 4 | 17:19
2019-02-05 | 14:45 | 15:50 | 1:05 | Research | Sprint 1 | FxRuby Library, Modular windows. | Sprint 5 | 8:29
2019-02-07 | 14:00 | 15:40 | 1:40 | Design | Sprint 1 | Code Architecture, Abstract Classes | Sprint 6
2019-02-08 | 11:00 | 14:00 | 3:00 | Code | Sprint 1 | Canvas Class(class creation, particular focus on canvas display | Project Total
2019-02-12 | 11:30 | 17:20 | 5:50 | Code | Sprint 1 | Group Class integration, testing, debugging
2019-02-18 | 14:00 | 17:10 | 3:10 | Code | Sprint 2 | Canvas Class(created display handlers for window resizing.
2019-02-19 | 14:00 | 16:50 | 2:50 | Architecture | Sprint 2 | FXRuby Event Handlers(researched and designed handlers for canvas update using SEL_Paint)
2019-02-21 | 14:00 | 17:05 | 3:05 | Code | Sprint 2 | Canvas Class(Implemented event handlers for canvas update)
2019-02-23 | 14:00 | 17:00 | 3:00 | Testing | Sprint 2 | Canvas Class( Debugged and tested canvas class)
2019-03-04 | 10:45 | 13:12 | 2:27 | Prototyping | Sprint 3 | Prototyped event handlers for mutli-sized brushes. Was unsuccesful.
2016-03-09 | 15:26 | 20:13 | 4:47 | Research | Sprint 3 | Research event handler hierarchy. Focus on built in SEL_Command methods.
2019-03-10 | 14:00 | 17:08 | 3:08 | Testing | Sprint 3 | Test newly made handlers. Mutli-tool unsuccessful, but line and point drawings successful.
2019-03-12 | 13:30 | 16:36 | 3:06 | Testing. | Sprint 3 | Integrated group changes into master class for final product before sprint presentation.
2019-03-30 | 15:49 | 17:28 | 1:39 | Design | Sprint 4 | Designing bitmap and PNG classes for storage and export of canvas data.
2019-04-01 | 17:00 | 22:35 | 5:35 | Prototyping | Sprint 4 | Prototyped nested event handlers for updating png files. PNG file initializes but is empty.
2019-04-05 | 10:00 | 13:31 | 3:31 | Testing | Sprint 4 | Tested PNG Export. Exports successfully.
2019-04-06 | 14:06 | 17:32 | 3:26 | Prototyping | Sprint 4 | Prototyping Event handlers for updating png files. Unsuccessful
2019-04-08 | 14:15 | 17:23 | 3:08 | Testing | Sprint 4 | Tested Canvas resize bug fix. Dirty resize does not work. Will make canvas static size.
2019-04-16 | 10:00 | 13:00 | 3:00 | Design | Sprint 5 | Designing architecture to store layer data and use that data to update the image export file.
2019-04-18 | 12:15 | 15:32 | 3:17 | Testing | Sprint 5 | Fix bugs associated with larger brush event handlers. Integrated brush handlers to edit image data.
2019-04-24 | 14:10 | 16:22 | 2:12 | Testing | Sprint 5 | Final testing and debug of sprint integration, including event handlers for canvas resize and new canvas methods.
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00